## Summary Dashboard
Migration Progress Dashboard — HOME
METRIC | VALUE | VISUAL PROGRESS | TARGET / NOTE
Total Methods / Elements Tracked | 36 | 100.0% complete | Target: 100%
Converted to Playwright | 36 | CONVERTED | Overall Playwright conversion progress
Partially Converted | 0 | PARTIAL | Dual implementation / partial work
Still Selenium / Pending | 0 | SELENIUM / PENDING | Requires code migration
% DONE (Playwright) | 100% |  | Converted / Total * 100
% PARTIAL | 0% |  | Partial / Total * 100
% PENDING (Selenium) | 0% |  | Pending / Total * 100
@Test METHODS — HOME ONLY
METHOD | STATUS | EXPECTED INVOCATIONS | NOTE
errorAndPageValidationScenario | PENDING | 0 | DP ApplicantHomeErrorDataProvider rows=0
getHomeQuote | PENDING | 0 | DP ApplicantHomeDataProvider currently resolves 0 rows (getListOfLegacyHomeStates returns empty list)
legacyHomeQuoteUsingAOR | PENDING | 31 | DP MonetizedLegacyHomeApplicantDataProvider rows=31; test is local-only
saveAndRetrieveHomeQuotes | PENDING | 0 | DP GetRetrieveQuoteApplicantHome currently resolves 0 rows (depends on empty legacy-home state list)
validateStateForHome | PENDING | 50 | DP StatesDataProvider rows=50
validateStateForLegacyHomeUsingAOR | PENDING | 2 | DP OneApplicantPerState invocations=2; test is local-only
validatesOneUiHomeContractMarkers | PENDING | 1 | No DataProvider (single invocation)
@Test Methods (total) | 7 | Total TestNG invocations (when all pass) | 84
PHASE 2 TIMELINE
Week / Period | HOME Component(s) | Number of Items | Description / Priority
Week 1 | DataProviders + HOME task execution gates | 2 | Restore legacy-home state list and confirm non-local execution behavior — BLOCKERS
Week 1-2 | HOME @Test deterministic invocation controls | 2 | Standardize stateList/home.case selectors and validate repeatable invocation counts — HIGH
Week 2 | OneUI/Legacy navigation stabilization | 2 | Harden AboutYou->ContactInfo and ContactInfo->Dwelling recovery checkpoints — MEDIUM
Week 3 | HOME suite stability pass | 7 | Re-run all HOME methods with deterministic data to collect pass evidence — FINAL
CRITICAL BLOCKERS (must fix first)
Component | Severity | Why it blocks HOME | Required fix
DataProviders.getListOfLegacyHomeStates | BLOCKERS | Returns empty list, so ApplicantHomeDataProvider and GetRetrieveQuoteApplicantHome resolve 0 rows in default regression path. | Populate valid legacy-home states per environment so HOME data providers emit executable rows.
legacyHomeQuoteUsingAOR + validateStateForLegacyHomeUsingAOR | BLOCKERS | Both methods hard-gate execution to remote=local; non-local runs are skipped, reducing HOME executable coverage. | Remove or parameterize local-only gate once environment routing contract is approved.

## Migration Status
HOME — Selenium → Playwright Full Migration Tracker
Category | Class / File | Method / Element (Playwright Target) | Selenium Method (Original / Current) | Status | Notes | Conversion Plan | Plan Start Date | Plan End Date | Total Days Expected | Actual Start Date | Actual End Date | Total Effort Days | Comments
Test Lifecycle | AutomationFramework.java | startPlaywrightTest(Method) | Selenium @BeforeMethod WebDriver setup | ✅ CONVERTED | PlaywrightSession starts test and binds Page/Context runtime. | No action required; maintain Playwright lifecycle hooks.
Test Lifecycle | AutomationFramework.java | finishPlaywrightTest(ITestResult) | Selenium @AfterMethod teardown/screenshot hooks | ✅ CONVERTED | Playwright final screenshot and trace lifecycle managed in AfterMethod. | No action required; maintain failure status capture.
Test Lifecycle | AutomationFramework.java | closePlaywrightWorker() | Selenium driver.quit() worker cleanup | ✅ CONVERTED | Thread-scoped Playwright worker shutdown replaces WebDriver quit. | No action required.
@Test Methods | ErrorAndValidationScenario.java | errorAndPageValidationScenario(ApplicantHome) | Legacy Selenium Home validation flow | ✅ CONVERTED | Runtime path uses Playwright locators/pages only. | No Selenium migration work pending for this method. | [6 empty] | Execution evidence currently pending/unstable.
@Test Methods | QuoteScenarios.java | getHomeQuote(ApplicantHome) | Legacy Selenium quote flow orchestration | ✅ CONVERTED | Dispatches Home flow through Playwright legacy/OneUI handlers. | No Selenium migration work pending for this method. | [6 empty] | DataProvider currently yields 0 rows in default regression config.
@Test Methods | QuoteScenarios.java | legacyHomeQuoteUsingAOR(ApplicantHome) | Legacy Selenium AOR navigation | ✅ CONVERTED | Playwright flow; gated to local remote only. | Keep Playwright path; remove local-only gate only if approved. | 2026-08-08 | 2026-08-12 | 5
@Test Methods | SaveAndRetrieveHomeQuoteScenarios.java | saveAndRetrieveHomeQuotes(ApplicantHome) | Legacy Selenium save/retrieve journey | ✅ CONVERTED | Uses Playwright Home pages and retrieve flow methods. | No Selenium migration work pending for this method. | [6 empty] | DataProvider currently yields 0 rows in default regression config.
@Test Methods | StateScenarios.java | validateStateForHome(State) | Legacy Selenium state validation | ✅ CONVERTED | Playwright path across Landing/Home/Knockout validation pages. | No Selenium migration work pending for this method. | [6 empty] | Invocation count driven by stateValidation worksheet rows.
@Test Methods | StateScenarios.java | validateStateForLegacyHomeUsingAOR(ApplicantHome) | Legacy Selenium AOR state check | ✅ CONVERTED | Playwright path; local-only execution guard still present. | Keep Playwright path; remove local-only guard only if approved. | 2026-08-08 | 2026-08-12 | 5
@Test Methods | HomeLocatorContractTests.java | validatesOneUiHomeContractMarkers() | N/A (new contract assertion) | ✅ CONVERTED | Pure Java fixture assertions; no Selenium runtime dependency. | No Selenium migration work pending for this method. | [6 empty] | Single invocation test.
DataProviders | DataProviders.java | applicantHome(Method) | Selenium-era Home data source selection | ✅ CONVERTED | Provider is Java/Excel based; no Selenium API use. | Populate legacy-home state list to enable invocations. | 2026-08-08 | 2026-08-12 | 5
DataProviders | DataProviders.java | applicantHomeErrorValidation() | Selenium-era Home error-row provider | ✅ CONVERTED | Provider returns ApplicantHome filtered by errorScenario=DISABLED. | No Selenium migration work pending.
DataProviders | DataProviders.java | aorHomeApplicant(Method) | Selenium-era AOR provider/filtering | ✅ CONVERTED | Provider filters monetized legacy states and optional home.case selectors. | No Selenium migration work pending.
DataProviders | DataProviders.java | getRetrieveQuoteHome(Method) | Selenium-era retrieve provider | ✅ CONVERTED | Provider uses Excel + state filters; no Selenium API use. | Populate legacy-home state list to enable invocations. | 2026-08-08 | 2026-08-12 | 5
DataProviders | SqlDataProviders.java | state(Method) [StatesDataProvider] | Selenium-era state iteration provider | ✅ CONVERTED | Provider is Java/Excel based with randomized ZIP assignment. | No Selenium migration work pending.
DataProviders | DataProviders.java | getListOfLegacyHomeStates(String) | Legacy state gate used by Home providers | ✅ CONVERTED | Method currently returns empty list, causing zero rows for some Home tests. | Populate supported legacy home states per environment. | 2026-08-08 | 2026-08-12 | 5
DataProviders | DataProviders.java | getListOfLegacyHomeMonetizedStates(String) | Legacy monetized-state resolution | ✅ CONVERTED | Returns NJ/NY for regression/test routing fallback. | No Selenium migration work pending.
Home Pages | LandingPage.java | enterLandingPageDataAndContinue(String,String) | driver.findElement/sendKeys/click flow | ✅ CONVERTED | Uses Playwright Locator/page interactions for landing submission. | No Selenium migration work pending. | [6 empty] | Shared page used by HOME runtime path.
Home Pages | YourInfoPageHome.java | enterYourInfoAndContinue(ApplicantHome,boolean,FarmersSoftAssert) | Selenium Your Info entry & continue | ✅ CONVERTED | Playwright locators, waits, and page transition checks. | No Selenium migration work pending.
Home Pages | PropertyPage.java | enterPropertyInfo(ApplicantHome,FarmersSoftAssert) | Selenium Property page interactions | ✅ CONVERTED | Playwright-based field entry and continue action. | No Selenium migration work pending.
Home Pages | ChooseYourCoveragePage.java | enterChooseYourCoveragePage(ApplicantHome,FarmersSoftAssert) | Selenium coverage package selection | ✅ CONVERTED | Playwright locators and dropdown/radio interactions. | No Selenium migration work pending.
Home Pages | QuotePageHome.java | enterQuotePage(ApplicantHome,FarmersSoftAssert) | Selenium quote page continuation | ✅ CONVERTED | Playwright continuation path and quote-page branching logic. | No Selenium migration work pending.
Home Pages | ThankYouPage.java | verifyThankYouPageContent(ApplicantHome,FarmersSoftAssert) | Selenium final-page assertions | ✅ CONVERTED | Assertions are executed through Playwright-derived page objects. | No Selenium migration work pending.
Home Pages | YourInfoPageHome.java | onYourInfoPageHome() | Selenium isOn page guard | ✅ CONVERTED | Visibility/path detection uses Playwright locators. | No Selenium migration work pending.
Home Pages | KnockoutInconveniencePage.java | isQuoteKnockedOut() | Selenium knockout presence checks | ✅ CONVERTED | Knockout/inconvenience detection uses Playwright locators. | No Selenium migration work pending.
Navigation Helpers | QuoteScenarios.java | dispatchHomeFlowForQuoteCreation(ApplicantHome,FarmersSoftAssert) | Legacy Selenium branch routing | ✅ CONVERTED | HomeFlowRouter-based Playwright flow dispatch (LEGACY/ONE_UI/etc.). | No Selenium migration work pending.
Navigation Helpers | AceHomeNavigationHelper.java | resumeFromAngularComponent(String) | Selenium URL/title resume logic | ✅ CONVERTED | Component-based resume routing for OneUI flow. | No Selenium migration work pending.
Navigation Helpers | AceHomeNavigationHelper.java | navigateToAceHomeContactInfoPage(ApplicantAceHome,String,String) | Selenium click/wait transition from About You | ✅ CONVERTED | Playwright transition wrapped with HomeRecoveryManager. | No Selenium migration work pending.
Navigation Helpers | AceHomeNavigationHelper.java | navigateToAceHomeReviewQuotePage(ApplicantAceHome,String,String) | Selenium chained navigation to review quote | ✅ CONVERTED | Playwright chained navigation via Ace HRC page objects. | No Selenium migration work pending.
Helper Classes | HomeFlowRouter.java | detect() | N/A (new Playwright flow detector) | ✅ CONVERTED | Inspects URL/components/headings/buttons using Playwright Page/Locator. | No Selenium migration work pending.
Helper Classes | HomeRecoveryManager.java | performRecoverableNavigation(...) | N/A (new Playwright recovery helper) | ✅ CONVERTED | Performs Try again recovery using Playwright role locator. | No Selenium migration work pending. | [6 empty] | Recovery exhausted can still fail functional execution.
BasePage Shared | BasePage.java | waitForSpinnerToBeGone() | Selenium spinner wait utilities | ✅ CONVERTED | Shared wait utility now Playwright-based and used by HOME pages. | No Selenium migration work pending.
BasePage Shared | BasePage.java | clearOutFieldUsingBackSpace(Locator) | Selenium clear/sendKeys backspace helper | ✅ CONVERTED | Shared field-clear helper accepts Playwright Locator. | No Selenium migration work pending.
BasePage Shared | BasePage.java | clickContinueButton() | Selenium click wrapper | ✅ CONVERTED | Shared continue click wrapper uses Playwright scroll+click. | No Selenium migration work pending.
Config | build.gradle | homeTest task include com/farmers/ffq/home/**/*.class | Selenium-specific suite wiring | ✅ CONVERTED | Dedicated HOME task exists and targets Home package classes only. | No Selenium migration work pending.
Config | build.gradle | systemProperties passthrough for home.case.zip/home.case.index | Selenium-era JVM arg wiring | ✅ CONVERTED | HOME selector properties are passed to Test JVM for deterministic AOR row selection. | No Selenium migration work pending.

## Column Legend
Column Definitions & Status Legend
Column | Definition
Category | Migration category for HOME-only execution surface (Test Lifecycle, @Test Methods, DataProviders, Home Pages, BasePage Shared, Navigation Helpers, Helper Classes, Config).
Class / File | Exact Java class or configuration file in the repository.
Method / Element (Playwright Target) | Specific method/element tracked as migration unit for HOME execution.
Selenium Method (Original) | Original Selenium pattern/behavior replaced or represented by current implementation.
Status | ✅ CONVERTED, ⚠ PARTIAL, ❌ SELENIUM classification.
Notes | Current technical behavior and runtime relevance.
Conversion Plan | Actionable migration/completion steps for this unit.
Plan Start Date | Planned start date for pending work.
Plan End Date | Planned completion date for pending work.
Total Days Expected | Estimated duration for planned work item.
Actual Start Date | Verified actual start date (blank when unverifiable).
Actual End Date | Verified actual completion date (blank when unverifiable).
Total Effort Days | Verified actual effort days (blank when unverifiable).
Comments | Additional execution impact, blockers, or context.
STATUS LEGEND
✅ CONVERTED | Method is fully Playwright. No Selenium imports/calls in HOME runtime execution path.
⚠ PARTIAL | Method has Playwright implementation but still has Selenium fallback/dependency or inconsistent runtime injection.
❌ SELENIUM | Method still uses Selenium exclusively in HOME runtime path and must be migrated.
MIGRATION PRIORITY ORDER
1. CRITICAL BLOCKERS
2. CONSTRUCTOR FIXES
3. isOnXxxPage() / visibility methods
4. NAVIGATION METHODS
5. INTERACTION METHODS
6. SHARED BasePage METHODS
7. XML & GRADLE