## Summary Dashboard
📊 Migration Progress Dashboard — AutoToAutoHomeBundleTestPlaywright
METRIC | VALUE | VISUAL PROGRESS | TARGET / NOTE
📦 Total Methods / Elements Tracked | 86 |  | —
✅ Converted to Playwright | 28 | ████████████ | 32.6%
⚠️ Partially Converted | 6 | ▒▒▒ | 7.0%
❌ Still Selenium / Pending | 52 | ░░░░░░░░░░░░░░░░░░░░░░ | 60.5%
📈 % DONE (Playwright) | 32.6% | Overall Playwright conversion progress | 🎯 Target: 100%
📈 % PARTIAL | 7.0% | Dual-impl methods; need Page injection fix only | 🔧 Quick wins
📈 % PENDING (Selenium) | 60.5% | Requires code migration | ⚠️ Active work needed
🧪 @Test Methods (total) | 3
✅ PASSING — validateAutoToMonoLineAutoFromInterstitialPage | 1 | ⭐ PROTECTED & FROZEN | 1 TestNG invocation
❌ PENDING — validateAutoToBundleHomeFlowFromInterstitialPage | 1 | Estimated ready: Aug 5, 2026 | 1 TestNG invocation
❌ PENDING — validateAutoHomeBundleFlowFromAutoQuoteSummaryPage | 1 | Estimated ready: Aug 18, 2026 | 1 TestNG invocation
📊 Total TestNG invocations (when all pass) | 3 | 3 invocations × 1 each | All DataProviders → 1 row each
📅 PHASE 2 TIMELINE
Week 1 (Jul 17–21) Fix DataProviders + AceBundleTestHelper | 2 items | Critical blockers → unblock both pending tests | 🔴 BLOCKERS
Week 2 (Jul 22–25) AceAutoNavigationHelper + AutoEnterAddressPage | 4 items | Full address flow Playwright migration | 🔴 HIGH
Week 3 (Jul 26–31) InterstitialBundlePage + Vehicles + HeresWhatWe Found | 8 items | Interstitial + HWWF + navigateBack() | 🟡 MEDIUM
Week 4 (Aug 1–7) ContactInfoAutoPage + QuoteSummaryAutoPage + completePurchase | 12 items | Quote summary + payment override | 🟡 MEDIUM
Week 5 (Aug 8–11) AceHRCPropertyTypeBasePage + Test 2 stabilization | 4 items | Property type + Test 2 E2E pass | 🟢 LOW
Week 6 (Aug 12–18) Test 3 stabilization + XML update + Full class run | 3 items | Test 3 E2E pass + XML + final regression | 🟢 FINAL
🚨 CRITICAL BLOCKERS (must fix first)
1. AceBundleDataProviders calls Property.getUri() | ❌ CRITICAL | Triggers Selenium AutomationFramework static init | Fix: System.getProperty("uri")
2. AceBundleTestHelper extends AutomationFramework | ❌ CRITICAL | Instantiation triggers WebDriver setup | Fix: Create PlaywrightBundleTestHelper
3. AutoDataProviders static field → Property.getTestProperty() | ❌ CRITICAL | Class load triggers Selenium framework | Fix: System.getProperty("stateList","")
4. AceBundleNavigationHelper called with no-arg ctor (page=null) | ❌ CRITICAL | NPE on all Playwright calls | Fix: use new AceBundleNavigationHelper(page, type)
5. testng-playwright.xml excludes pending tests | ❌ CRITICAL | Tests silently not run via Gradle | Fix: remove <include> method filter

## Migration Status
🎭 AutoToAutoHomeBundleTestPlaywright — Selenium → Playwright Full Migration Tracker
Category | Class / File | Method / Element (Playwright Target) | Selenium Method (Original / Current) | Status | Notes | Conversion Plan | Plan Start Date | Plan End Date | Total Days Expected | Actual Start Date | Actual End Date | Total Effort Days | Comments
🏗️ Test Lifecycle | PlaywrightBaseTest | startPlaywright() [@BeforeClass] | WebDriver driver = new ChromeDriver() / DriverFactory.getDriver() in @BeforeClass | ✅ CONVERTED | Launches Chromium via Playwright.create(); headless=false by default; browser/context/page are instance fields | COMPLETED — No action required | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | Fully Playwright; no Selenium dependency
🏗️ Test Lifecycle | PlaywrightBaseTest | createBrowserContextAndPage() [@BeforeMethod] | driver.get(url); WebDriverWait wait = new WebDriverWait(driver, Duration.ofSeconds(30)) | ✅ CONVERTED | Creates BrowserContext + Page per test; sets default timeouts 30 s / 60 s | COMPLETED — No action required | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | Fully Playwright; no Selenium dependency
🏗️ Test Lifecycle | PlaywrightBaseTest | closeBrowserContext() [@AfterMethod] | driver.quit(); @AfterMethod teardown; ExtentReports screenshot via TakesScreenshot | ✅ CONVERTED | Captures failure screenshot (page.screenshot); stops Playwright tracing; closes context | COMPLETED — No action required | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | Fully Playwright; no Selenium dependency
🏗️ Test Lifecycle | PlaywrightBaseTest | stopPlaywright() [@AfterClass] | driver.quit() / DriverFactory cleanup in @AfterClass | ✅ CONVERTED | Closes Playwright browser and Playwright instance; null-guards prevent double-close | COMPLETED — No action required | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | 2026-06-05 06:00 | 2026-06-06 06:00 | 1 | Fully Playwright; no Selenium dependency
🏗️ Test Lifecycle | PlaywrightTestSupport | testStepAssert(boolean, String) | AutomationFramework.testStepAssert() — delegates to Reporter.pass/fail + WebDriver screenshot | ✅ CONVERTED | Pure TestNG Assert wrapper with console logging; no browser dependency | COMPLETED — No action required | 2026-06-01 06:00 | 2026-06-02 06:00 | 1 | 2026-06-01 06:00 | 2026-06-02 06:00 | 0.5 | Zero Selenium; safe for Playwright tests
🏗️ Test Lifecycle | PlaywrightTestSupport | testStepAssertTrue(boolean, String) | AutomationFramework.testStepAssert() — same signature in Selenium base | ✅ CONVERTED | Pure TestNG Assert wrapper; no browser dependency | COMPLETED — No action required | 2026-06-01 06:00 | 2026-06-02 06:00 | 1 | 2026-06-01 06:00 | 2026-06-02 06:00 | 0.5 | Zero Selenium; safe for Playwright tests
🏗️ Test Lifecycle | PlaywrightTestSupport | driver() stub — throws UnsupportedOperationException | AutomationFramework.driver() → returns ThreadLocal WebDriver instance | ✅ CONVERTED | Compile-time stub that throws at runtime; prevents accidental Selenium WebDriver calls in Playwright tests | COMPLETED — Stub already in place; guards against regression | 2026-06-01 06:00 | 2026-06-02 06:00 | 1 | 2026-06-01 06:00 | 2026-06-02 06:00 | 0.5 | Critical safety net; do not remove
🏗️ Test Lifecycle | PlaywrightBaseTest | updateApplicantDataToAvoidPossibleBw(AutoApplicant) | AutomationFramework.updateApplicantDataToAvoidPossibleBw() — same logic in Selenium base | ✅ CONVERTED | Pure data mutation (setIncidents, setHaveAccidentOrViolations, etc.); no browser interaction | COMPLETED — No action required | 2026-06-10 06:00 | 2026-06-10 06:00 | 1 | 2026-06-10 06:00 | 2026-06-10 06:00 | 0.5 | Identical logic duplicated in PlaywrightBaseTest to avoid Selenium superclass init
🏗️ Test Lifecycle | PlaywrightBaseTest | randomizeApplicantPersonalData(AutoApplicant) | AutomationFramework.randomizeApplicantPersonalData() — same logic in Selenium base | ✅ CONVERTED | Pure data mutation (Faker first/last name, DOB, email); no browser interaction | COMPLETED — No action required | 2026-06-10 06:00 | 2026-06-10 06:00 | 1 | 2026-06-10 06:00 | 2026-06-10 06:00 | 0.5 | Identical logic duplicated in PlaywrightBaseTest to avoid Selenium superclass init
🏗️ Test Lifecycle | PlaywrightBaseTest | completePurchase() — base placeholder | BaseTest.completePurchase() — full Selenium checkout: PaymentSelectionPage, CardPaymentPage, etc. | ✅ CONVERTED | Throws UnsupportedOperationException; forces subclass override; prevents accidental Selenium checkout | COMPLETED — Placeholder in place; concrete override needed in test class (see completePurchase @Override row) | 2026-06-10 06:00 | 2026-06-10 06:00 | 1 | 2026-06-10 06:00 | 2026-06-10 06:00 | 0.5 | Base is safe; override in test class still uses Selenium ctors
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | validateAutoToMonoLineAutoFromInterstitialPage(AutoApplicant) | AutoToAutoHomeBundleTest.validateAutoToMonoLineAutoFromInterstitialPage() — Selenium: LandingPage.enterLandingPageData(), radio click via WebElement | ✅ CONVERTED | ⭐ PROTECTED & FROZEN. Full Playwright flow: zip fill, Auto option detection (7 locator strategies + iframe fallback), navigation assertion. 1 TestNG invocation. | COMPLETED — PROTECTED. Do NOT modify under any circumstances. | 2026-07-01 06:00 | 2026-07-10 06:00 | 10 | 2026-07-01 06:00 | 2026-07-10 06:00 | 8 | PASSING. Regression check must run after every shared dependency change.
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | setOwnOrRentHomeInAceBundleApplicantAsOwned(AceBundleApplicant) | AutoToAutoHomeBundleTest.setOwnOrRentHomeInAceBundleApplicantAsOwned() — same pure data mutation | ✅ CONVERTED | Pure data mutation: applicant.getAutoApplicant().getDiscounts().forEach(i -> i.setOwnOrRentHome("Own a home")). No browser interaction. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-05 06:00 | 1 | 2026-07-05 06:00 | 2026-07-05 06:00 | 0.5 | Zero browser dependency
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | setOwnOrRentHomeInApplicantAsOwned(AutoApplicant) | AutoToAutoHomeBundleTest.setOwnOrRentHomeInApplicantAsOwned() — same pure data mutation | ✅ CONVERTED | Pure data mutation on discount objects. No browser interaction. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-05 06:00 | 1 | 2026-07-05 06:00 | 2026-07-05 06:00 | 0.5 | Zero browser dependency
📊 DataProviders | AutoToAutoHomeBundleTestPlaywright | singleAutoApplicant() @DataProvider | AutoDataProviders.autoApplicantsIterator() — uses ExcelDataProvider from framework JAR + Property.getTestProperty("stateList") static init | ✅ CONVERTED | Reads OneUIAutoTestData.xlsx via FileInputStream / XSSFWorkbook (Apache POI). Filters AZ + applicantId=1. Returns 1 random invocation. Zero framework dependency. | COMPLETED — Local Excel-based implementation in test class; no Selenium dependency | 2026-07-05 06:00 | 2026-07-08 06:00 | 3 | 2026-07-05 06:00 | 2026-07-08 06:00 | 2.5 | Clean Playwright DP. Depends on OneUIAutoTestData.xlsx being present.
📊 DataProviders | AutoToAutoHomeBundleTestPlaywright | listOfAutoApplicantsLocal(String, String) | AutoDataProviders.listOfAutoApplicants() — ExcelDataProvider.readExcelData() from framework JAR | ✅ CONVERTED | Local Apache POI read of applicant + vehicles + additionalDriver + incidents + discounts sheets. Pure Java. No framework dependency. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-08 06:00 | 3 | 2026-07-05 06:00 | 2026-07-08 06:00 | 2 | Replaces framework SQL/Excel provider with clean local implementation
📊 DataProviders | AutoToAutoHomeBundleTestPlaywright | readSheetRows(String sheetName) | ExcelDataProvider.readExcelData(sheetName) from automation-framework JAR | ✅ CONVERTED | Reads Apache POI XSSFWorkbook sheet into List<Map<String,String>>. No framework dependency. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-08 06:00 | 3 | 2026-07-05 06:00 | 2026-07-08 06:00 | 1 | Key utility; used by all local data helpers
📊 DataProviders | AutoToAutoHomeBundleTestPlaywright | mapRowToObject(Class<T>, Map<String,String>) | DataObjectBase.mapFromRow() from framework JAR using PropertyUtils | ✅ CONVERTED | Reflection-based field mapper using field.set(). Handles String, int, boolean, double, Enum types. Pure Java. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-08 06:00 | 3 | 2026-07-05 06:00 | 2026-07-08 06:00 | 1 | Replaces framework PropertyUtils mapper
📊 DataProviders | AutoToAutoHomeBundleTestPlaywright | getAllVehiclesLocal() / getAllAdditionalDriversLocal() / getAllIncidentsLocal() / getAllDiscountsLocal() | SqlDataProviders.getVehiclesByApplicantId() + SQL queries via JDBC from automation-framework | ✅ CONVERTED | Local Excel reads of "vehicles", "additionalDriver", "incidents", "discounts" sheets via readSheetRows(). No SQL, no JDBC, no framework. | COMPLETED — No action required | 2026-07-05 06:00 | 2026-07-08 06:00 | 3 | 2026-07-05 06:00 | 2026-07-08 06:00 | 1.5 | Replaces SQL data providers with pure Excel reads
📄 Auto Pages | InterstitialBundlePage | InterstitialBundlePage(Page page) constructor | N/A — new Playwright-only constructor, no Selenium equivalent | ✅ CONVERTED | Page-injection constructor exists at line 37: super(page). Passes Page to AutoBasePage for Playwright-aware operations. | COMPLETED — Constructor exists and is Playwright-ready | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.5 | Use this constructor from all Playwright test callers
📄 Auto Pages | VehiclesDriversInfoPage | VehiclesDriversInfoPage(Page page) constructor | N/A — new Playwright-only constructor | ✅ CONVERTED | Page-injection constructor exists at line 66: super(page). Playwright-ready. | COMPLETED — Constructor exists | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.5 | Use this constructor from all Playwright test callers
📄 Auto Pages | HeresWhatWeFoundPage | HeresWhatWeFoundPage(Page page) constructor | N/A — new Playwright-only constructor | ✅ CONVERTED | Page-injection constructor available (inherits through WhoShouldWeInsurePage). Playwright-ready. | COMPLETED — Constructor exists | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.5 | Use this constructor from all Playwright test callers
📄 ACE HRC Pages | AceHRCPropertyTypeBasePage | AceHRCPropertyTypeBasePage(Page page) constructor | N/A — new Playwright-only constructor | ✅ CONVERTED | Page-injection constructor exists at line 48. Calls super(page) which passes to AceHRCBasePage → BasePage. | COMPLETED — Constructor exists | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.5 | Use this constructor from all Playwright test callers
🎯 AceBundleNavHelper | AceBundleNavigationHelper | AceBundleNavigationHelper(Page, String) constructor | N/A — new Playwright-only constructor; old Selenium ctor: AceBundleNavigationHelper(String) → super() → WebDriver init | ✅ CONVERTED | Playwright constructor at line 1147: Objects.requireNonNull(page,...); calls super(page); stores Page field. Full Playwright implementation. | COMPLETED — Constructor exists and is Playwright-ready | 2026-07-01 06:00 | 2026-07-15 06:00 | 15 | 2026-07-01 06:00 | 2026-07-15 06:00 | 12 | Use new AceBundleNavigationHelper(page, AUTO_HOME_BUNDLE) in @Test methods
🎯 AceBundleNavHelper | AceBundleNavigationHelper | setResumeFromPage() / setBundleType() / setBundleQuoteNumber() | Same Lombok-generated setters in old Selenium class | ✅ CONVERTED | Lombok @Setter generates these. No browser dependency. Works in both Selenium and Playwright context. | COMPLETED — No action required | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.25 | Pure data setters; zero browser dependency
🎯 AceBundleNavHelper | AceBundleNavigationHelper | navigateToECheckoutPage(AceBundleApplicant) | Old Selenium impl (lines 1-1083, commented out): AceHRCPaymentSelectionPage (Selenium), PolicyPaymentBasePage (Selenium), debit/credit card entry via WebElement | ✅ CONVERTED | New Playwright impl at line 1179. Creates all page objects with (page) injection. Uses TimeoutError catch + NavigationException. Full Playwright flow including payment selection and card entry. | COMPLETED — New Playwright implementation is in place after line 1085 | 2026-07-01 06:00 | 2026-07-15 06:00 | 15 | 2026-07-01 06:00 | 2026-07-15 06:00 | 12 | The old Selenium code is preserved in the block comment /* */ for reference (lines 1-1083)
🎯 AceBundleNavHelper | AceBundleNavigationHelper | navigateToPayForPropertyPage(AceBundleApplicant) | Old Selenium impl (in block comment): AceHRCPaymentSelectionPage (Selenium), various HRC Selenium page objects | ✅ CONVERTED | New Playwright impl. Creates AceHRCPaymentSelectionPage(page) with injection. Uses page-aware waitForCondition(). Full Playwright. | COMPLETED — New Playwright implementation is in place | 2026-07-01 06:00 | 2026-07-15 06:00 | 15 | 2026-07-01 06:00 | 2026-07-15 06:00 | 10 | Part of Playwright checkout navigation chain
🎯 AceBundleNavHelper | AceBundleNavigationHelper | navigateToPayForAutoPage(AceBundleApplicant) | Old Selenium impl (in block comment): AceBundleAutoPaymentPage (Selenium), auto payment form interactions | ✅ CONVERTED | New Playwright impl. Creates AceBundleAutoPaymentPage(page). Uses Playwright assertions and waits. | COMPLETED — New Playwright implementation is in place | 2026-07-01 06:00 | 2026-07-15 06:00 | 15 | 2026-07-01 06:00 | 2026-07-15 06:00 | 8 | Part of Playwright checkout navigation chain
🧾 completePurchase Override | EcheckoutSuccessfulPageOneUI | EcheckoutSuccessfulPageOneUI(Page page) constructor | N/A — new Playwright-only constructor | ✅ CONVERTED | Page-injection constructor exists at line 43. Playwright-ready. | COMPLETED — Constructor exists | 2026-07-01 06:00 | 2026-07-01 06:00 | 1 | 2026-07-01 06:00 | 2026-07-01 06:00 | 0.5 | Use this constructor in completePurchase() override
📊 DataProviders | AutoDataProviders | updateApplicantsForBind(List<AutoApplicant>) | AutoDataProviders.updateApplicantsForBind() — same method; calls listOfAutoApplicants() internally which uses ExcelDataProvider from framework | ⚠️ PARTIAL | Method body is pure data mutation (Faker name, email, phone, random address from same state). HOWEVER AutoDataProviders class-level static field calls Property.getTestProperty("stateList") on class load, triggering Selenium framework init the moment AutoDataProviders is referenced. | 1. Guard static field: replace static { Property.getTestProperty("stateList") } with lazy-loaded System.getProperty("stateList", "") 2. Replace listOfAutoApplicants() call inside updateApplicantsForBind() with local Excel reader or inline address data 3. After fix: method is fully safe for Playwright use | 2026-07-17 06:00 | 2026-07-19 06:00 | 3 |  |  |  | Fix static initializer first. Body logic is already Playwright-compatible once class loads cleanly.
📄 Auto Pages | VehiclesDriversInfoPage | getListOfSteps() [inherited from BasePage] | driver().findElements(By.xpath(NAV_BAR_STEPPER_XPATH)) → List<WebElement> → stream().map(getTextFromElement) | ⚠️ PARTIAL | BasePage.getListOfSteps() already has if(page!=null) Playwright branch using page.locator(desktopXpath).allTextContents(). However, with no-arg constructor (page=null), the Selenium branch executes. FIX: inject Page via Playwright constructor. | 1. No code change needed in BasePage.getListOfSteps() — Playwright branch already implemented 2. FIX ONLY: use new VehiclesDriversInfoPage(page) instead of new VehiclesDriversInfoPage() 3. Once Page is injected, the if(page!=null) branch fires automatically | 2026-07-28 06:00 | 2026-07-28 06:00 | 1 |  |  |  | PARTIAL — Playwright branch EXISTS. Fix is solely in the constructor call site (pass page).
📄 Auto Pages | QuoteSummaryAutoPage | closeQualtricsPopUp() [inherited from BasePage] | if (areElementsDisplayed(listOfQualtricsCloseButtons, 3)) waitAndClickElement(listOfQualtricsCloseButtons.get(0)) — Selenium List<WebElement> | ⚠️ PARTIAL | BasePage.closeQualtricsPopUp() ALREADY has if(page!=null) Playwright branch: page.locator(closeXpath).first().click() if visible. Works correctly when Page is injected. With no-arg ctor (page=null), the Selenium branch executes. | 1. No code change needed in BasePage.closeQualtricsPopUp() — Playwright branch already implemented at line 2145-2153 2. FIX ONLY: use new QuoteSummaryAutoPage(page) instead of new QuoteSummaryAutoPage() 3. Once Page is injected, the if(page!=null) branch fires automatically | 2026-08-04 06:00 | 2026-08-04 06:00 | 1 |  |  |  | PARTIAL — Playwright branch EXISTS. Fix is solely in the constructor call site.
📦 BasePage Shared | BasePage | getListOfSteps() | driver().findElements(By.xpath(NAV_BAR_STEPPER_XPATH + "/descendant::*[contains(@class,'tui-step-label')]")) → stream().map(getTextFromElement) | ⚠️ PARTIAL | ALREADY has if(page!=null) Playwright branch: page.locator(desktopXpath).allTextContents(). Returns clean list of step labels. Playwright path is correct and complete. Only fires when page is injected via Playwright constructor. | NO CODE CHANGE NEEDED in BasePage.getListOfSteps() ACTION: Fix constructor call sites to inject Page (new VehiclesDriversInfoPage(page), etc.) Once page != null, Playwright branch fires automatically. | 2026-07-28 06:00 | 2026-07-28 06:00 | 1 |  |  |  | PARTIAL — Playwright impl EXISTS. Activation depends solely on Page injection in constructor call sites.
📦 BasePage Shared | BasePage | closeQualtricsPopUp() | if (areElementsDisplayed(listOfQualtricsCloseButtons, 3)) waitAndClickElement(listOfQualtricsCloseButtons.get(0)) — Selenium List<WebElement> | ⚠️ PARTIAL | ALREADY has if(page!=null) Playwright branch: page.locator(closeXpath).first().click() if visible. Correct and complete Playwright implementation at line 2145-2153. Only fires when page is injected. | NO CODE CHANGE NEEDED in BasePage.closeQualtricsPopUp() ACTION: Fix constructor call sites to inject Page Once page != null, Playwright branch fires automatically. | 2026-08-04 06:00 | 2026-08-04 06:00 | 1 |  |  |  | PARTIAL — Playwright impl EXISTS. Activation depends solely on Page injection.
⚙️ Config | testng-playwright.xml | <include name="validateAutoToMonoLineAutoFromInterstitialPage"/> only | N/A — XML config file; not a Selenium method | ⚠️ PARTIAL | testng-playwright.xml currently uses <include> filter to run ONLY the protected method. Tests 2 & 3 are silently excluded from Gradle playwrightTest run even though they are in the class. | 1. Option A (recommended): Remove the <methods> / <include> block entirely — let TestNG discover all @Test methods in the class 2. Option B: Add <include> entries for the 2 pending tests once they pass 3. Update suite name and test name to reflect full class scope 4. Verify with: gradlew playwrightTest --tests "...AutoToAutoHomeBundleTestPlaywright" | 2026-08-18 06:00 | 2026-08-18 06:00 | 1 |  |  |  | Final step of Phase 2. Only update XML after all 3 tests pass. Removing the filter exposes all @Test methods to Gradle.
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | validateAutoToBundleHomeFlowFromInterstitialPage(AceBundleApplicant) | AutoToAutoHomeBundleTest.validateAutoToBundleHomeFlowFromInterstitialPage() — full Selenium: AceAutoNavigationHelper (Selenium), InterstitialBundlePage (WebElement), VehiclesDriversInfoPage, AceBundleNavigationHelper (Selenium) | ❌ SELENIUM | Uses AceBundleTestHelper (extends AutomationFramework), AceAutoNavigationHelper (Selenium), 5+ Selenium page objects. DataProvider blocked by Property.getUri(). 1 TestNG invocation expected. | 1. Fix AceBundleDataProviders DP (Property.getUri → System.getProperty) 2. Fix AceBundleTestHelper (no Selenium superclass) 3. Migrate AceAutoNavigationHelper.navigateToAutoEnterAddressPage() 4. Migrate AutoEnterAddressPage.fillOutAddressPage() 5. Migrate InterstitialBundlePage (isOn + continue) 6. Migrate VehiclesDriversInfoPage / HeresWhatWeFoundPage 7. Fix AceBundleNavigationHelper ctor (pass page) 8. Run, stabilize, regression-check protected method | 2026-07-17 06:00 | 2026-08-05 06:00 | 14 |  |  |  | BLOCKED by 5 critical Selenium dependencies. Estimated 12–16 days after Phase 2 approval.
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | validateAutoHomeBundleFlowFromAutoQuoteSummaryPage(AceBundleApplicant) | AutoToAutoHomeBundleTest.validateAutoHomeBundleFlowFromAutoQuoteSummaryPage() — full Selenium: AceAutoNavigationHelper, ContactInfoAutoPage, QuoteSummaryAutoPage, AceHRCPropertyTypeBasePage (all Selenium) | ❌ SELENIUM | Uses AceBundleTestHelper (extends AutomationFramework), AceAutoNavigationHelper, 4+ Selenium page objects. DataProvider blocked by Property.getUri(). 1 TestNG invocation expected. | 1. Fix shared blockers (same as Test 2 steps 1-2) 2. Migrate AceAutoNavigationHelper.navigateToEitherQuoteSummaryPage() 3. Migrate ContactInfoAutoPage (isOn + uncheckBundle + clickContinue) 4. Migrate QuoteSummaryAutoPage (isOn + closeQualtrics + checkBundle + navigateBack + clickBundle) 5. Migrate AceHRCPropertyTypeBasePage.isOnPropertyTypePage() 6. Fix AceBundleNavigationHelper ctor (pass page) 7. Run, stabilize, regression-check protected method | 2026-08-04 06:00 | 2026-08-18 06:00 | 11 |  |  |  | Partially overlaps Test 2 dependencies. Estimated 10–14 days after Test 2 is stable.
🧪 @Test Methods | AutoToAutoHomeBundleTestPlaywright | completePurchase() @Override | BaseTest.completePurchase() → ConsolidatedPaymentPage (Selenium), BwPaymentSummaryPage (Selenium), EcheckoutSuccessfulPageOneUI (Selenium no-arg ctor) | ❌ SELENIUM | Creates BwPaymentSummaryPage(), ConsolidatedPaymentPage(), EcheckoutSuccessfulPageOneUI() via no-arg Selenium constructors. BW page check and payment processing are Selenium-only. | 1. Change new BwPaymentSummaryPage() → new BwPaymentSummaryPage(page) 2. Migrate BwPaymentSummaryPage.isOnBristolWest() to Playwright 3. Change new ConsolidatedPaymentPage() → new ConsolidatedPaymentPage(page) 4. Migrate ConsolidatedPaymentPage.processConsolidatedPaymentPage() to Playwright 5. Change new EcheckoutSuccessfulPageOneUI() → new EcheckoutSuccessfulPageOneUI(page) 6. Migrate waitForSpinnerToBeGone(), isSignElectronicallyPresent(), signDocuments() | 2026-08-01 06:00 | 2026-08-10 06:00 | 8 |  |  |  | Called indirectly by AceBundleNavigationHelper checkout flow. Must complete before full bind E2E works.
📊 DataProviders | AceBundleDataProviders | bundleApplicantsIterator() @DataProvider (for Tests 2 & 3) | AceBundleDataProviders.bundleApplicantsIterator() — calls Property.getUri() (Selenium framework), AutoDataProviders.listOfAutoApplicants() (static init), DataProviders.listOfAceHomeApplicants() (ExcelDataProvider from JAR) | ❌ SELENIUM | CRITICAL BLOCKER. Property.getUri() triggers AutomationFramework static initializer before any browser starts. Also calls AutoDataProviders which has static field calling Property.getTestProperty("stateList") on class load. | 1. Replace Property.getUri() with System.getProperty("uri", "https://ffqautouiuat.farmers.com/fastquote/") 2. Replace getListOfAceBundleStates(uri) with inline env detection or a Playwright-safe utility 3. Replace AutoDataProviders.listOfAutoApplicants() call with a local Excel reader (similar to singleAutoApplicant DP pattern) 4. Replace DataProviders.listOfAceHomeApplicants() with local AceHomeTestData.xlsx reader 5. Keep applicantId=1 filter + RANDOM_BUNDLE_APPLICANT selection logic intact 6. Validate 1 invocation per test | 2026-07-17 06:00 | 2026-07-19 06:00 | 3 |  |  |  | Must be fixed FIRST before either pending test can start. Blocks both Tests 2 and 3.
📊 DataProviders | AutoDataProviders | listOfAutoApplicants(String, String) [internal call from AceBundleDataProviders] | AutoDataProviders.listOfAutoApplicants() → ExcelDataProvider.readExcelData("OneUIAutoTestData.xlsx") from automation-framework JAR | ❌ SELENIUM | Called by AceBundleDataProviders. Depends on ExcelDataProvider from the Selenium framework JAR. Class static init also calls Property.getTestProperty("stateList"). | 1. Replace ExcelDataProvider.readExcelData() call with local FileInputStream/XSSFWorkbook reader (same pattern as readSheetRows() already written) 2. Fix static field to use System.getProperty instead of Property.getTestProperty 3. This fix is shared across both pending test DataProviders | 2026-07-17 06:00 | 2026-07-19 06:00 | 3 |  |  |  | This is a transitive fix. Fixing AceBundleDataProviders (above) will naturally address this dependency.
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | AceAutoNavigationHelper() constructor | new AceAutoNavigationHelper() → super() → AutoBasePage() → BasePage() → AutomationFramework() → PageFactory.initElements(driver(), this) | ❌ SELENIUM | No-arg constructor calls super() up the Selenium inheritance chain. AutomationFramework init fires WebDriver. @FindBy WebElement progressbarAceAuto is injected by PageFactory. | 1. Add AceAutoNavigationHelper(Page page) constructor that calls super(page) and stores page 2. In @Test methods use: new AceAutoNavigationHelper(page) instead of new AceAutoNavigationHelper() 3. Remove @FindBy WebElement progressbarAceAuto or replace with Playwright Locator field | 2026-07-20 06:00 | 2026-07-22 06:00 | 3 |  |  |  | Constructor fix is prerequisite for ALL AceAutoNavigationHelper method migrations
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | processLandingPage(AutoApplicant) | LandingPage.enterLandingPageData(LOB_AUTO, applicant.getZipCode()) → Selenium: WebElement radio click, form fill via @FindBy, explicit waits | ❌ SELENIUM | Creates Selenium LandingPage. Enters zip and selects LOB_AUTO using @FindBy WebElement interactions. LandingPage uses ExpectedConditions + WebDriverWait. | 1. In Playwright path: use page.navigate(uri), page.locator("input[aria-label='Zip code']").fill(zip), auto-selection logic (already exists in protected test validateAutoToMonoLineAutoFromInterstitialPage — extract as shared helper) 2. Replace LandingPage with direct Playwright locator interactions 3. Consider extracting navigateToLandingPage(Page, AutoApplicant) helper method | 2026-07-20 06:00 | 2026-07-24 06:00 | 5 |  |  |  | The landing page Playwright logic already exists in the protected test. Reuse that logic.
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | navigateToNameAndDobPage(AutoApplicant) | NameAndDobPage namePage = new NameAndDobPage() → Selenium @FindBy fields; filloutApplicantForm() via WebElement interactions | ❌ SELENIUM | Creates NameAndDobPage (Selenium). Fills first name, last name, DOB using @FindBy WebElement fields. | 1. Add NameAndDobPage(Page page) constructor if not present 2. Replace page object creation: new NameAndDobPage(page) 3. Migrate NameAndDobPage.filloutApplicantForm() to Playwright locators (getByLabel/getByRole for input fields) 4. Replace waitForSpinnerToBeGone() with Playwright spinner locator.waitFor(HIDDEN) | 2026-07-22 06:00 | 2026-07-24 06:00 | 3 |  |  |  | Intermediate step in the address navigation chain
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | navigateToAutoEnterAddressPage(AutoApplicant) | new AutoEnterAddressPage() → isOnEnterAddressPage() → isElementVisible(@FindBy WebElement, 20s) — Selenium | ❌ SELENIUM | Creates no-arg AutoEnterAddressPage. Checks isOnEnterAddressPage() via Selenium isElementVisible(). No Page injection. | 1. Change: AutoEnterAddressPage autoEnterAddressPage = new AutoEnterAddressPage(page) 2. Migrate AutoEnterAddressPage.isOnEnterAddressPage() to: page.locator("div[class*='personal-info_address_h1']").waitFor(VISIBLE) 3. Remove Selenium page object creation throughout this method | 2026-07-22 06:00 | 2026-07-25 06:00 | 4 |  |  |  | Used by Test 2. Depends on AutoEnterAddressPage(Page) constructor being added.
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | navigateToEitherQuoteSummaryPage(AutoApplicant) | Full Selenium chain: navigateToWhoShouldWeInsureOrHeresWhatWeFoundPage() → WhoShouldWeInsurePage (Selenium) → HeresWhatWeFoundPage (Selenium) → ContactInfoAutoPage (Selenium) → QuoteSummaryAutoPage (Selenium) | ❌ SELENIUM | Chains multiple Selenium page object navigations. All page objects created with no-arg constructors. All assertions via isElementVisible / isElementPresent with Selenium WebElements. | 1. Create Playwright navigation path: after landing → name/DOB → address → on-moment → HWWF/WSUI → driver review → coverage → contact info → quote summary 2. For each page in the chain: use page.waitForURL() or locator.waitFor(VISIBLE) instead of isElementPresent 3. Add Page injection to all page objects in the chain 4. Use page.getByRole / page.locator with stable CSS selectors | 2026-07-25 06:00 | 2026-08-02 06:00 | 9 |  |  |  | Most complex migration. Entire auto quote navigation chain. Used by Test 3.
🗺️ AceAutoNavigationHelper | AceAutoNavigationHelper | processHeresWhatWeFoundOrVehicleDriverConsolidatedPage(AutoApplicant) | HeresWhatWeFoundPage.processPage() + VehiclesDriversInfoPage interactions — all Selenium @FindBy WebElement operations | ❌ SELENIUM | Interacts with the vehicle/driver review page. Checks/unchecks vehicle and driver checkboxes. Clicks continue. All via Selenium WebElement list iterations. | 1. Migrate vehicle/driver checkbox interactions to Playwright: page.locator("//mat-checkbox").all() → for each locator.check()/uncheck() 2. Replace isElementVisible() checks with locator.isVisible() 3. Replace waitAndClickElement(continueButton) with page.locator(".continue-button").click() 4. Remove PageFactory / @FindBy dependencies | 2026-07-28 06:00 | 2026-08-01 06:00 | 5 |  |  |  | Used by Test 2. Can reuse VehiclesDriversInfoPage(page) constructor once migrated.
📄 Auto Pages | AutoEnterAddressPage | AutoEnterAddressPage() no-arg constructor | new AutoEnterAddressPage() → PageFactory.initElements(driver(), this) → WebDriver WebElement injection for 15+ @FindBy fields | ❌ SELENIUM | No-arg constructor triggers AutoBasePage() → BasePage() → AutomationFramework() chain. PageFactory injects 15+ @FindBy WebElement fields using the active Selenium WebDriver. | 1. Add: public AutoEnterAddressPage(Page page) throws Exception { super(page); } if not present 2. In all callers: replace new AutoEnterAddressPage() with new AutoEnterAddressPage(page) 3. Verify super(page) correctly stores the Playwright Page in BasePage.page field | 2026-07-22 06:00 | 2026-07-22 06:00 | 1 |  |  |  | Quick win: constructor is likely just adding a one-liner. Prerequisite for all address page method migrations.
📄 Auto Pages | AutoEnterAddressPage | fillOutAddressPage(AutoApplicant) | Selenium: waitAndClickElement(enterAddressManuallyLink), sendKeys() to manualStreetInputField (@FindBy WebElement), selectDropdown(townDropDown), waitAndClickElement(continueButton) | ❌ SELENIUM | Fills street address, city, zip, apt, state via @FindBy WebElement fields. Handles autocomplete dropdown, manual entry mode, recent mover popup, and zip-change confirmation dialog — all via Selenium. | 1. Replace @FindBy fields with Playwright locators: - enterAddressManuallyLink → page.locator("//span[@class='manual-addr-heading']//a") - manualStreetInputField → page.locator("//div[@id='formField_street']//input") - continueButton → page.locator(ADDRESS_PAGE_CONTINUE_BUTTON_XPATH) 2. Replace sendKeys() with locator.fill() 3. Replace selectDropdown() with page.selectOption() or locator.click() + option click 4. Replace explicit waits with Playwright auto-wait (locator.fill() already waits for actionability) | 2026-07-22 06:00 | 2026-07-25 06:00 | 4 |  |  |  | Complex method; handles multiple UI variants. Largest single-method migration in the address flow.
📄 Auto Pages | AutoEnterAddressPage | isOnEnterAddressPage() | isElementVisible(addressPageTitle, 20) where addressPageTitle is @FindBy(xpath="//div[contains(@class,'personal-info_address_h1')]") WebElement | ❌ SELENIUM | Selenium WebDriverWait visibility check on @FindBy WebElement. Returns boolean. | 1. Replace with: page.locator("//div[contains(@class,'personal-info_address_h1')]").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(20000)) 2. Return true after waitFor succeeds (or wrap in try/catch for boolean return) | 2026-07-22 06:00 | 2026-07-22 06:00 | 1 |  |  |  | Simple 1-locator conversion. Pattern is identical to 10+ other isOnXxxPage() methods.
📄 Auto Pages | InterstitialBundlePage | InterstitialBundlePage() no-arg constructor | new InterstitialBundlePage() → PageFactory.initElements(driver(), this) → injects 8 @FindBy WebElement fields | ❌ SELENIUM | No-arg constructor triggers full Selenium init chain. PageFactory injects 8 @FindBy fields. | 1. Page-injection constructor already exists: InterstitialBundlePage(Page page) at line 37 2. In all callers: replace new InterstitialBundlePage() with new InterstitialBundlePage(page) 3. No new constructor code needed — just fix call sites | 2026-07-26 06:00 | 2026-07-26 06:00 | 1 |  |  |  | Constructor already available. Only call sites need updating.
📄 Auto Pages | InterstitialBundlePage | isOnInterstitialBundlePage() | isElementVisible(pageHeader, 10) where pageHeader is @FindBy(id="bundlePageHeaderTitle") WebElement | ❌ SELENIUM | Selenium WebDriverWait + ExpectedConditions.visibilityOf(pageHeader). Returns boolean. | 1. Replace with: page.locator("#bundlePageHeaderTitle").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(10000)) 2. Return true (waitFor throws on timeout) 3. Or use PlaywrightAssertions.assertThat(page.locator("#bundlePageHeaderTitle")).isVisible() | 2026-07-26 06:00 | 2026-07-26 06:00 | 1 |  |  |  | Standard isOnPage() pattern. Quick 1-locator conversion.
📄 Auto Pages | InterstitialBundlePage | continueWithBundle() | waitAndClickElement(continueWithBundleDiscountButton) where button is @FindBy(xpath="//div[@class='bundle-page__bundle-continue-button']//button") WebElement | ❌ SELENIUM | Selenium explicit wait + WebElement.click(). waitAndClickElement() also handles stale element retry. | 1. Replace with: page.locator("//div[@class='bundle-page__bundle-continue-button']//button").click() 2. Playwright auto-waits for actionability (visible + enabled) before clicking 3. Remove @FindBy continueWithBundleDiscountButton field | 2026-07-26 06:00 | 2026-07-26 06:00 | 1 |  |  |  | Simple click conversion. Playwright auto-wait replaces explicit Selenium wait.
📄 Auto Pages | InterstitialBundlePage | waitForSpinnerToBeGone() [inherited from AutoBasePage] | WebDriverWait.until(ExpectedConditions.invisibilityOfElementLocated(By.css(".spinner"))) — inherited from BasePage/AutoBasePage | ❌ SELENIUM | Selenium explicit wait for spinner invisibility. Used after continueWithBundle() and other async operations. | 1. Replace with: page.locator(".spinner, [class*=spinner], [class*=loading]").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.HIDDEN).setTimeout(30000)) 2. Or use page.waitForLoadState(LoadState.NETWORKIDLE) for full page stabilization 3. Add Playwright-aware implementation to AutoBasePage.waitForSpinnerToBeGone() | 2026-07-26 06:00 | 2026-07-27 06:00 | 2 |  |  |  | Shared method on AutoBasePage. Fix once; all page objects benefit.
📄 Auto Pages | VehiclesDriversInfoPage | VehiclesDriversInfoPage() no-arg constructor | new VehiclesDriversInfoPage() → PageFactory.initElements(driver(), this) → injects 25+ @FindBy / @FindAll WebElement fields | ❌ SELENIUM | No-arg constructor triggers Selenium chain. PageFactory injects 25+ WebElement fields. Extends HeresWhatWeFoundPage → WhoShouldWeInsurePage → AutoBasePage → BasePage → AutomationFramework. | 1. VehiclesDriversInfoPage(Page page) constructor exists at line 66 2. In all callers: replace new VehiclesDriversInfoPage() with new VehiclesDriversInfoPage(page) 3. No new constructor code needed | 2026-07-28 06:00 | 2026-07-28 06:00 | 1 |  |  |  | Page-injection constructor already available. Only call sites need updating.
📄 Auto Pages | VehiclesDriversInfoPage | isOnVehiclesDriversInfoPage() | isElementVisible(vehiclesDriversPageTitle, 20) where vehiclesDriversPageTitle is @FindBy(xpath="//app-vehicles-drivers-main-screen//h1") WebElement | ❌ SELENIUM | Selenium WebDriverWait visibility check. 20-second timeout. Returns boolean. | 1. Replace with: page.locator("//app-vehicles-drivers-main-screen//h1").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(20000)) 2. Return true / wrap in try/catch for boolean return | 2026-07-28 06:00 | 2026-07-28 06:00 | 1 |  |  |  | Standard isOnPage() pattern conversion.
📄 Auto Pages | VehiclesDriversInfoPage | navigateBack() [inherited from BasePage] | driver().navigate().back(); waitForSpinnerToBeGone() — Selenium WebDriver browser.navigate().back() | ❌ SELENIUM | BasePage.navigateBack() calls driver().navigate().back() then waitForSpinnerToBeGone(). No Playwright branch exists in BasePage for navigateBack(). | 1. Add Playwright branch to BasePage.navigateBack(): if (page != null) { page.goBack(); page.waitForLoadState(DOMCONTENTLOADED); return; } 2. Keep existing Selenium path for non-migrated callers 3. After page injection is fixed, the Playwright branch will fire automatically | 2026-07-28 06:00 | 2026-07-29 06:00 | 2 |  |  |  | BasePage.navigateBack() is a shared method. Fix once; all migrated page objects benefit automatically.
📄 Auto Pages | HeresWhatWeFoundPage | HeresWhatWeFoundPage() no-arg constructor | new HeresWhatWeFoundPage() → PageFactory.initElements(driver(), this) → injects 30+ @FindBy/@FindAll WebElement fields via Selenium chain | ❌ SELENIUM | No-arg constructor triggers Selenium init. Extends WhoShouldWeInsurePage → AutoBasePage. PageFactory injects 30+ fields. | 1. HeresWhatWeFoundPage(Page page) constructor check: likely available (similar to VehiclesDriversInfoPage) 2. In all callers: replace new HeresWhatWeFoundPage() with new HeresWhatWeFoundPage(page) | 2026-07-29 06:00 | 2026-07-29 06:00 | 1 |  |  |  | Fix constructor call site; Playwright path opens automatically for page-aware methods.
📄 Auto Pages | HeresWhatWeFoundPage | isOnHeresWhatWeFoundPage() | isElementVisible(heresWhatWeFoundPageHeader, 55) where header is @FindBy(xpath="//h1[contains(...)]") WebElement — 55-second timeout | ❌ SELENIUM | Selenium WebDriverWait with 55-second timeout. Checks for page heading visibility. | 1. Replace with: page.locator("//h1[contains(@class,'auto-vehicles-drivers-review__heading tui-h1') or contains(text(),'what we found')]").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(55000)) 2. Return true (waitFor throws on timeout) | 2026-07-29 06:00 | 2026-07-29 06:00 | 1 |  |  |  | Long 55-second timeout — preserve in Playwright equivalent.
📄 Auto Pages | HeresWhatWeFoundPage | navigateBack() [inherited from BasePage] | driver().navigate().back(); waitForSpinnerToBeGone() | ❌ SELENIUM | Same as VehiclesDriversInfoPage.navigateBack() — inherited BasePage method. Calls driver().navigate().back(). | 1. Already covered by BasePage.navigateBack() fix (add if(page!=null) Playwright branch) 2. No additional action needed once BasePage.navigateBack() is fixed | 2026-07-29 06:00 | 2026-07-29 06:00 | 1 |  |  |  | Shared fix with VehiclesDriversInfoPage. One BasePage change covers both.
📄 Auto Pages | WhoShouldWeInsurePage | WhoShouldWeInsurePage() no-arg constructor [class name only — getSimpleName() usage] | new WhoShouldWeInsurePage() → heavy Selenium: By, FindAll, FindBy, WebDriverWait, ExpectedConditions, Actions; 50+ @FindBy fields | ❌ SELENIUM | In Tests 2 & 3, WhoShouldWeInsurePage is only instantiated to get its class name (getSimpleName()) for setResumeFromPage(). The no-arg constructor still fires Selenium init unnecessarily. | 1. Option A (simplest): Replace new WhoShouldWeInsurePage().getClass().getSimpleName() with the string literal "WhoShouldWeInsurePage" 2. Option B: Add WhoShouldWeInsurePage(Page page) constructor and use new WhoShouldWeInsurePage(page) 3. Option A is recommended — avoids needless page object init for a simple class name lookup | 2026-07-30 06:00 | 2026-07-30 06:00 | 1 |  |  |  | Quick win: replace instantiation-for-classname with string literal.
📄 Auto Pages | ContactInfoAutoPage | ContactInfoAutoPage() no-arg constructor | new ContactInfoAutoPage() → PageFactory.initElements(driver(), this) → 40+ @FindBy WebElement fields injected via Selenium chain | ❌ SELENIUM | No-arg constructor fires Selenium chain through AutoBasePage. PageFactory injects 40+ WebElement fields. Used in Test 3. | 1. Add: public ContactInfoAutoPage(Page page) throws Exception { super(page); } if not present 2. In Test 3: replace new ContactInfoAutoPage() with new ContactInfoAutoPage(page) 3. Or declare field: ContactInfoAutoPage contactInfoAutoPage = new ContactInfoAutoPage(page) | 2026-08-01 06:00 | 2026-08-01 06:00 | 1 |  |  |  | Constructor one-liner. Prerequisite for all ContactInfoAutoPage method migrations.
📄 Auto Pages | ContactInfoAutoPage | isOnContactInfoAutoPage() | isElementVisible(pageHeaderNote, 25) where pageHeaderNote is @FindBy(xpath="//div[contains(@class,'contact-info-heading-note')]") WebElement — 25-second timeout | ❌ SELENIUM | Selenium WebDriverWait visibility check on @FindBy WebElement. 25-second timeout. | 1. Replace with: page.locator("//div[contains(@class,'contact-info-heading-note')]").waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(25000)) 2. Return true after waitFor | 2026-08-01 06:00 | 2026-08-01 06:00 | 1 |  |  |  | Standard isOnPage() pattern. Quick conversion.
📄 Auto Pages | ContactInfoAutoPage | uncheckAllTheBundleCheckbox() | for (WebElement saveBundleInput : saveBundleInputs) { if(isButtonSelected(saveBundleInput)) scrollAndClickOnElement(waitElementBeVisible(saveBundleInput)); } — Selenium WebElement list iteration | ❌ SELENIUM | Iterates List<WebElement> saveBundleInputs (@FindBy). For each checked input, calls Selenium scroll + click. Uses isButtonSelected() (getAttribute("aria-checked")). | 1. Replace with: Locator inputs = page.locator("//div[@class='save-bundle-discount-sheet']//mat-checkbox//input") 2. for (int i=0; i<inputs.count(); i++) { if (inputs.nth(i).isChecked()) inputs.nth(i).uncheck(); } 3. Playwright uncheck() auto-waits and scrolls into view | 2026-08-01 06:00 | 2026-08-02 06:00 | 2 |  |  |  | Checkbox list iteration — straightforward Playwright Locator.nth() pattern.
📄 Auto Pages | ContactInfoAutoPage | clickContinueButton() | clickContactInfoPageCTAButton() → waitAndClickElement(@FindBy WebElement agreeAndSubmitButton / continueButton) | ❌ SELENIUM | Selenium waitAndClickElement with @FindBy WebElement. Internal method clickContactInfoPageCTAButton() handles A/B tested button variants. | 1. Replace with: page.locator("button:has-text('Agree and submit'), button:has-text('Continue')").first().click() 2. Playwright first() handles multiple matching elements; auto-waits for actionability | 2026-08-02 06:00 | 2026-08-02 06:00 | 1 |  |  |  | Button click with variant handling. Use :has-text() CSS pseudo-class for resilience.
📄 Auto Pages | QuoteSummaryAutoPage | QuoteSummaryAutoPage() no-arg constructor | new QuoteSummaryAutoPage() → PageFactory.initElements(driver(), this) → 80+ @FindBy/@FindAll WebElement fields; By, Actions, ExpectedConditions in class body | ❌ SELENIUM | No-arg constructor fires Selenium chain. One of the heaviest page objects: 80+ @FindBy fields, By locators, Actions chains. Used in Test 3. | 1. Add: public QuoteSummaryAutoPage(Page page) throws Exception { super(page); } if not present 2. In Test 3: replace new QuoteSummaryAutoPage() with new QuoteSummaryAutoPage(page) 3. Only migrate the 6 specific methods called by Test 3 — do not attempt full class migration | 2026-08-04 06:00 | 2026-08-04 06:00 | 1 |  |  |  | Very large class. Migrate ONLY the 6 methods needed by Test 3. Full class migration is out of scope.
📄 Auto Pages | QuoteSummaryAutoPage | isOnQuoteSummaryAutoPage() | isElementPresent(By.xpath("//app-coverage[not(@class)] ¦ //app-quote//h1[contains(@class, 'page-title')]"), 45) — Selenium driver().findElements(By) | ❌ SELENIUM | Selenium driver().findElements() with 45-second timeout. Checks for coverage section or page title heading. | 1. Replace with: page.locator("//app-coverage[not(@class)]").or(page.locator("//app-quote//h1[contains(@class,'page-title')]")).first().waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(45000)) 2. Return true after waitFor | 2026-08-04 06:00 | 2026-08-04 06:00 | 1 |  |  |  | 45-second timeout preserved. Playwright locator.or() replaces XPath union.
📄 Auto Pages | QuoteSummaryAutoPage | checkBundleOrContinueToAutoButtonNotDisplayed(FarmersSoftAssert) | driver().findElements(By.partialLinkText("Bundle and save")).size()==0 — Selenium driver().findElements(By) | ❌ SELENIUM | Calls driver().findElements(By.partialLinkText()) to verify bundle button is absent. Also checks startCheckoutButton.isDisplayed() via @FindBy WebElement. | 1. Replace driver().findElements(By.partialLinkText("Bundle and save")) with: page.locator("a:has-text('Bundle and save')").count() == 0 2. Replace startCheckoutButton.isDisplayed() with: page.locator("button:has-text('Continue')").isVisible() 3. Wrap in fsa assertions | 2026-08-04 06:00 | 2026-08-05 06:00 | 2 |  |  |  | Uses Playwright count() and isVisible() instead of Selenium findElements()
📄 Auto Pages | QuoteSummaryAutoPage | navigateBack() [inherited from BasePage] | driver().navigate().back(); waitForSpinnerToBeGone() | ❌ SELENIUM | Same BasePage.navigateBack() as all other pages. Calls driver().navigate().back(). | 1. Covered by BasePage.navigateBack() fix (add if(page!=null) Playwright branch) 2. No additional action needed in QuoteSummaryAutoPage | 2026-08-04 06:00 | 2026-08-04 06:00 | 1 |  |  |  | Shared BasePage fix covers this automatically.
📄 Auto Pages | QuoteSummaryAutoPage | checkBundleOrContinueToAutoButtonDisplayed(FarmersSoftAssert) | startCheckoutButton.isDisplayed() + driver().findElement(By.partialLinkText("Bundle and save")).isDisplayed() — Selenium WebElement + driver() | ❌ SELENIUM | Checks both "Continue with auto" button text and "Bundle and save" link are visible. Uses @FindBy WebElement and driver().findElement(By.partialLinkText()). | 1. Replace startCheckoutButton text check with: page.locator("button:has-text('Continue with auto')").isVisible() 2. Replace driver().findElement(By.partialLinkText("Bundle and save")) with: page.locator("a:has-text('Bundle and save')").isVisible() 3. Pass results to fsa assertions | 2026-08-05 06:00 | 2026-08-05 06:00 | 1 |  |  |  | Straightforward isVisible() conversion.
📄 Auto Pages | QuoteSummaryAutoPage | clickBundleAndContinueButton() | closeQualtricsPopUp(); waitAndClickElement(@FindBy WebElement bundleAndContinueButton) — Selenium click | ❌ SELENIUM | Dismisses Qualtrics popup then clicks "Bundle and save" / bundle continue button via @FindBy WebElement. | 1. closeQualtricsPopUp() fix already covered (Playwright branch in BasePage) 2. Replace waitAndClickElement(bundleAndContinueButton) with: page.locator("a:has-text('Bundle and save'), button:has-text('Bundle and save')").first().click() | 2026-08-05 06:00 | 2026-08-05 06:00 | 1 |  |  |  | Click conversion; relies on closeQualtricsPopUp() being Playwright-aware via page injection.
📄 ACE HRC Pages | AceHRCPropertyTypeBasePage | AceHRCPropertyTypeBasePage() no-arg constructor | new AceHRCPropertyTypeBasePage() → super() → AceHRCBasePage() → BasePage() → AutomationFramework() — Selenium chain | ❌ SELENIUM | No-arg constructor triggers full Selenium chain via AceHRCBasePage. @FindBy fields (pageTitle, propertyTypeCard, etc.) injected by PageFactory. | 1. AceHRCPropertyTypeBasePage(Page page) constructor already exists at line 48: super(page) 2. In Test 3: replace new AceHRCPropertyTypeBasePage() with new AceHRCPropertyTypeBasePage(page) | 2026-08-08 06:00 | 2026-08-08 06:00 | 1 |  |  |  | Page-injection constructor already available. Only call site needs fixing.
📄 ACE HRC Pages | AceHRCPropertyTypeBasePage | isOnPropertyTypePage() | isOnPageCheck(Property.PAGELOADTIMEOUT) → isElementPresent(By.xpath(PROPERTY_TYPE_CARD_XPATH), timeout) — Selenium driver().findElements(By) + framework Property.PAGELOADTIMEOUT constant | ❌ SELENIUM | Two Selenium dependencies: (1) isElementPresent uses driver().findElements(By), (2) Property.PAGELOADTIMEOUT requires Selenium framework init. | 1. Replace Property.PAGELOADTIMEOUT with system property or constant: int timeout = Integer.parseInt(System.getProperty("pageloadtimeout","30")) 2. Replace isElementPresent(By) with: page.locator(PROPERTY_TYPE_CARD_XPATH).waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.VISIBLE).setTimeout(timeout * 1000L)) 3. Return true after waitFor | 2026-08-08 06:00 | 2026-08-08 06:00 | 1 |  |  |  | Two fixes needed: Property constant and isElementPresent. Both are standard conversions.
🎯 AceBundleNavHelper | AceBundleNavigationHelper | AceBundleNavigationHelper(String) no-arg style | AceBundleNavigationHelper(String kindOfBundle) → super() → BasePage() → AutomationFramework() → PageFactory.initElements(driver(), this) | ❌ SELENIUM | No-arg-style constructor (String only) sets this.page = null and calls super() → Selenium chain. Any subsequent Playwright call on this instance will NPE since page is null. | 1. In Test 2 & 3: replace new AceBundleNavigationHelper(AUTO_HOME_BUNDLE) with new AceBundleNavigationHelper(page, AUTO_HOME_BUNDLE) 2. The Playwright constructor (Page, String) already exists at line 1147 3. No source change needed in AceBundleNavigationHelper itself | 2026-08-10 06:00 | 2026-08-10 06:00 | 1 |  |  |  | Quick fix: change 2 constructor call sites in the @Test methods from (String) to (page, String)
🧾 completePurchase Override | BwPaymentSummaryPage | BwPaymentSummaryPage() no-arg constructor | new BwPaymentSummaryPage() → extends AutoPolicyPaymentBasePage → AutoBasePage → BasePage → AutomationFramework → PageFactory.initElements(driver(), this) | ❌ SELENIUM | No-arg ctor fires Selenium chain. PageFactory injects 15+ @FindBy fields. Used in completePurchase() override to check if on Bristol West page. | 1. Add: public BwPaymentSummaryPage(Page page) throws Exception { super(page); } if not present 2. In completePurchase() override: replace new BwPaymentSummaryPage() with new BwPaymentSummaryPage(page) | 2026-08-01 06:00 | 2026-08-01 06:00 | 1 |  |  |  | Constructor one-liner. Prerequisite for isOnBristolWest() Playwright migration.
🧾 completePurchase Override | BwPaymentSummaryPage | isOnBristolWest() | isElementVisible(@FindBy WebElement pageHeader, timeout) or URL-based check — Selenium | ❌ SELENIUM | Checks whether the current page is the Bristol West payment summary. Used to route to BW vs standard payment flow. | 1. Replace with: boolean isBW = page.url().contains("payment-overview") && page.locator("//app-payment-overview//h1").isVisible() 2. Or: page.locator("[class*='bristolwest'], [class*='bristol-west']").count() > 0 | 2026-08-01 06:00 | 2026-08-02 06:00 | 2 |  |  |  | URL + locator check pattern. Fast and reliable in Playwright.
🧾 completePurchase Override | ConsolidatedPaymentPage | ConsolidatedPaymentPage() no-arg constructor | new ConsolidatedPaymentPage() → extends AutoPolicyPaymentBasePage → AutoBasePage → Selenium chain. PageFactory injects 20+ @FindBy/@FindAll fields | ❌ SELENIUM | No-arg ctor fires Selenium chain. Heavy Selenium usage: By, WebElement, ExpectedConditions, List<WebElement> for payment card interactions. | 1. Add: public ConsolidatedPaymentPage(Page page) throws Exception { super(page); } 2. In completePurchase() override: replace new ConsolidatedPaymentPage() with new ConsolidatedPaymentPage(page) | 2026-08-02 06:00 | 2026-08-02 06:00 | 1 |  |  |  | Constructor one-liner. Complex method migrations needed for processConsolidatedPaymentPage().
🧾 completePurchase Override | ConsolidatedPaymentPage | processConsolidatedPaymentPage(String, PaymentMethods, boolean) | Complex Selenium: radio button selections, credit/debit card form fill via @FindBy WebElements, PAY_IN_FULL vs MONTHLY_AUTOPAY branching, card number/expiry/CVV entry | ❌ SELENIUM | Complex payment flow: selects payment plan, fills card details (number, expiry, CVV, zip), handles EFT vs credit card branching. All via @FindBy WebElement interactions. | 1. Use page.locator() for payment plan radio buttons: page.locator("//mat-radio-button[contains(.,'" + paymentPlanOption + "')]").click() 2. Fill card fields: page.locator("input[aria-label='Card number']").fill(cardNumber), etc. 3. Handle PAY_IN_FULL vs MONTHLY_AUTOPAY branch with Playwright locator visibility checks 4. Replace ExpectedConditions with Playwright auto-wait | 2026-08-02 06:00 | 2026-08-07 06:00 | 6 |  |  |  | Highest complexity in completePurchase path. Multiple payment method variants must be handled.
🧾 completePurchase Override | EcheckoutSuccessfulPageOneUI | EcheckoutSuccessfulPageOneUI() no-arg constructor | new EcheckoutSuccessfulPageOneUI() → AutoBasePage → Selenium chain. @FindBy injected fields. | ❌ SELENIUM | No-arg ctor fires Selenium chain. Has Page-injection constructor at line 43 that is not being used in completePurchase() override. | 1. Page-injection constructor already exists: EcheckoutSuccessfulPageOneUI(Page page) at line 43 2. In completePurchase() override: replace new EcheckoutSuccessfulPageOneUI() with new EcheckoutSuccessfulPageOneUI(page) | 2026-08-07 06:00 | 2026-08-07 06:00 | 1 |  |  |  | Constructor already available. Quick call-site fix only.
🧾 completePurchase Override | EcheckoutSuccessfulPageOneUI | waitForSpinnerToBeGone() [inherited from AutoBasePage] | WebDriverWait.until(ExpectedConditions.invisibilityOfElementLocated(spinnerSelector)) — Selenium explicit wait | ❌ SELENIUM | Selenium explicit wait for spinner element to become invisible. Inherited from AutoBasePage. | 1. Covered by shared AutoBasePage.waitForSpinnerToBeGone() fix 2. Add Playwright branch: if (page != null) { page.locator(".spinner,...").waitFor(HIDDEN); return; } 3. Once Page is injected, Playwright branch fires automatically | 2026-08-07 06:00 | 2026-08-07 06:00 | 1 |  |  |  | Shared fix on AutoBasePage covers this and all other waitForSpinnerToBeGone() calls simultaneously.
🧾 completePurchase Override | EcheckoutSuccessfulPageOneUI | isSignElectronicallyPresent() | isElementVisible(@FindBy(xpath="//h1[contains(.,'Sign electronically')]") WebElement, timeout) — Selenium | ❌ SELENIUM | Checks if "Sign electronically" heading is visible. Used to decide whether to call signDocuments(). | 1. Replace with: page.locator("//h1[contains(.,'Sign electronically')]").isVisible() 2. Playwright isVisible() returns false immediately if not present (no timeout throw) | 2026-08-07 06:00 | 2026-08-07 06:00 | 1 |  |  |  | Simple isVisible() conversion. Playwright returns false vs Selenium returns false+timeout.
🧾 completePurchase Override | EcheckoutSuccessfulPageOneUI | signDocuments() | waitAndClickElement(@FindBy WebElement startSigningButton) — Selenium click via @FindBy(xpath="//button[@class='cta-sign']") | ❌ SELENIUM | Clicks the "Start signing" button to initiate e-signature. Single button click after payment success. | 1. Replace with: page.locator("//button[contains(@class,'cta-sign')]").click() 2. Playwright auto-waits for button actionability before clicking | 2026-08-07 06:00 | 2026-08-07 06:00 | 1 |  |  |  | Simple click conversion.
🔧 Helper Classes | AceBundleTestHelper | AceBundleTestHelper — class level | AceBundleTestHelper extends AutomationFramework — Selenium superclass with WebDriver, PageFactory, @FindBy, Reporter (Selenium) etc. | ❌ SELENIUM | CRITICAL BLOCKER. AceBundleTestHelper extends AutomationFramework (Selenium). Any instantiation triggers WebDriver setup. Also: applicantAdjustment() calls new AutoBasePage().getRandomVinNumber(3) — creates Selenium page object just to fetch a VIN. | 1. Create PlaywrightBundleTestHelper that does NOT extend AutomationFramework 2. Copy applicantAdjustment() logic verbatim 3. Replace new AutoBasePage().getRandomVinNumber(3) with: (a) a VIN API call via HttpClient, or (b) a hardcoded test VIN, or (c) set vehicle.useVIN=false when VIN lookup fails 4. In @Test methods: replace new AceBundleTestHelper() with new PlaywrightBundleTestHelper() 5. Keep original AceBundleTestHelper unchanged for Selenium tests | 2026-07-19 06:00 | 2026-07-22 06:00 | 4 |  |  |  | Must NOT modify AceBundleTestHelper (Selenium tests depend on it). Create new Playwright-specific version.
📦 BasePage Shared | BasePage | navigateBack() | driver().navigate().back(); waitForSpinnerToBeGone() — Selenium WebDriver navigation | ❌ SELENIUM | BasePage.navigateBack() has NO Playwright branch. Calls driver().navigate().back() unconditionally. Affects VehiclesDriversInfoPage, HeresWhatWeFoundPage, QuoteSummaryAutoPage, and ContactInfoAutoPage in the pending tests. | 1. Add Playwright branch at top of method: if (page != null) { page.goBack(); page.waitForLoadState(LoadState.DOMCONTENTLOADED); return; } 2. Keep existing Selenium path for non-migrated callers 3. Test with VehiclesDriversInfoPage.navigateBack() after page injection fix | 2026-07-29 06:00 | 2026-07-29 06:00 | 1 |  |  |  | HIGH IMPACT: one fix in BasePage covers navigateBack() for ALL page objects in pending tests simultaneously.
📦 BasePage Shared | BasePage | waitForSpinnerToBeGone() | WebDriverWait.until(ExpectedConditions.invisibilityOfElementLocated(By.id("jsAlert99_popup"))) or spinner CSS — Selenium | ❌ SELENIUM | Selenium explicit wait for spinner/loading overlay. Called after every navigation and page action. No Playwright branch. | 1. Add Playwright branch: if (page != null) { page.locator("#jsAlert99_popup, .spinner, [class*=loading-overlay]") .waitFor(new Locator.WaitForOptions().setState(WaitForSelectorState.HIDDEN).setTimeout(30000)); return; } 2. Keep Selenium path for non-migrated callers | 2026-07-27 06:00 | 2026-07-27 06:00 | 1 |  |  |  | HIGH IMPACT: one fix covers waitForSpinnerToBeGone() for ALL page objects simultaneously.
📦 BasePage Shared | BasePage | isElementVisible(WebElement, int) | WebDriverWait.until(ExpectedConditions.visibilityOf(webElement), timeout) — Selenium visibility check | ❌ SELENIUM | Core Selenium visibility method. Called by isOnXxxPage() methods in InterstitialBundlePage, VehiclesDriversInfoPage, HeresWhatWeFoundPage, ContactInfoAutoPage. Returns boolean. | Each isOnXxxPage() method should be individually migrated to use page.locator().waitFor(VISIBLE) instead of calling isElementVisible(). Do NOT add a Playwright branch to isElementVisible() itself — too risky to change the shared method. Migrate the callers one by one. | 2026-07-26 06:00 | 2026-08-08 06:00 | 14 |  |  |  | Do not change isElementVisible() globally — migrate each caller individually to Playwright locator.waitFor().
📦 BasePage Shared | BasePage | isElementPresent(By, int) | driver().findElements(By, timeout) — returns true if list is not empty — Selenium | ❌ SELENIUM | Used by isOnQuoteSummaryAutoPage(), isOnPropertyTypePage(), isOnContactInfoPage(). Returns true if element found within timeout. | Migrate each caller individually: - isOnQuoteSummaryAutoPage() → page.locator(xpath).first().waitFor(VISIBLE) - isOnPropertyTypePage() → page.locator(xpath).waitFor(VISIBLE) - isOnContactInfoAutoPage() → page.locator(xpath).waitFor(VISIBLE) Do NOT change isElementPresent() globally. | 2026-07-26 06:00 | 2026-08-08 06:00 | 14 |  |  |  | Same pattern as isElementVisible(). Migrate callers individually rather than changing the shared method.
📦 BasePage Shared | BasePage | waitAndClickElement(WebElement) | WebDriverWait.until(ExpectedConditions.elementToBeClickable(webElement)).click() — Selenium | ❌ SELENIUM | Selenium explicit wait for clickability then click. Called by continueWithBundle(), clickContinueButton(), clickBundleAndContinueButton(), etc. | Migrate each caller individually: - continueWithBundle() → page.locator(xpath).click() - clickBundleAndContinueButton() → page.locator(bundleXpath).click() - clickContinueButton() → page.locator(continueXpath).click() Playwright locator.click() already waits for actionability. No need to replicate waitAndClickElement(). | 2026-07-26 06:00 | 2026-08-08 06:00 | 14 |  |  |  | Playwright .click() auto-waits for actionability — no wrapper needed. Migrate callers individually.
🏗️ Test Lifecycle
🧪 @Test Methods
📊 DataProviders
🗺️ AceAutoNavigationHelper
📄 Auto Pages
📄 ACE HRC Pages
🎯 AceBundleNavHelper
🧾 completePurchase Override
🔧 Helper Classes
📦 BasePage Shared
⚙️ Config

## Column Legend
📋 Column Definitions & Status Legend
Column | Definition
Category | Functional grouping: Test Lifecycle, @Test Methods, DataProviders, page objects, config, etc.
Class / File | Java class name or configuration file where the method/element lives
Method / Element (Playwright Target) | The Playwright-based method being built or the target Playwright API equivalent
Selenium Method (Original) | The original Selenium-based method / API being replaced, including the specific Selenium calls used
Status | ✅ CONVERTED = fully Playwright, no Selenium dependency ⚠️ PARTIAL = dual impl; works when Page is injected via Playwright ctor ❌ SELENIUM = still Selenium; must be migrated
Notes | Technical context: what the method does, how many invocations, key risks
Conversion Plan | Step-by-step migration instructions specific to this method
Plan Start Date | Estimated start date for this migration task (Phase 2 planning)
Plan End Date | Estimated completion date for this migration task
Total Days Expected | Estimated calendar days for this specific migration task
Actual Start Date | (To be filled) Real date work began on this task
Actual End Date | (To be filled) Real date this task was completed and verified
Total Effort Days | (To be filled) Actual days of effort spent (may differ from calendar days)
Comments | Additional notes, dependencies, risks, or post-implementation observations
STATUS LEGEND
✅ CONVERTED | Method is fully Playwright. No Selenium imports or calls in its execution path. Has been verified to run without triggering Selenium WebDriver initialization.
⚠️ PARTIAL | Method has a dual Playwright+Selenium implementation protected by if(page != null). The Playwright branch is correct and complete. However, with a no-arg constructor (page = null), the Selenium branch executes at runtime. Fix: inject Page via the Playwright constructor.
❌ SELENIUM | Method uses Selenium exclusively (WebElement, @FindBy, driver(), WebDriverWait, ExpectedConditions, By, PageFactory, or AutomationFramework). This method MUST be migrated before the pending @Test can pass.
MIGRATION PRIORITY ORDER
1. CRITICAL BLOCKERS | Fix AceBundleDataProviders (Property.getUri), AutoDataProviders (static init), AceBundleTestHelper (AutomationFramework). These prevent tests from even starting.
2. CONSTRUCTOR FIXES | Pass Playwright Page to every page object via (Page page) constructor. Many constructors already exist — this is often a one-line call-site fix.
3. isOnXxxPage() METHODS | Replace isElementVisible / isElementPresent with page.locator().waitFor(VISIBLE). One-line conversions.
4. NAVIGATION METHODS | Replace driver().navigate().back() with page.goBack(). Add navigateBack() Playwright branch to BasePage once; all page objects inherit it.
5. INTERACTION METHODS | Replace waitAndClickElement / sendKeys with locator.click() / locator.fill(). Playwright auto-waits eliminate the need for explicit waits.
6. SHARED BasePage METHODS | Add if(page!=null) Playwright branches to waitForSpinnerToBeGone() and navigateBack() in BasePage. One fix covers all migrated page objects.
7. XML & GRADLE | Remove <include> method filter in testng-playwright.xml after all 3 tests pass.