## Summary Dashboard
Migration Progress Dashboard — HOME / AUTO
METRIC | HOME | AUTO | TARGET / NOTE
Primary E2E | homeDomHappyPathE2E | bristolWestE2EDeterministic | Integrated acceptance E2E scenarios
Integration status | INTEGRATED | INTEGRATED | Both scenarios are integrated in ffq-master-playwright
Playwright Java | YES | YES | Shared AutomationFramework / PlaywrightSession; no Selenium runtime
Compile / structural validation | PASS (offline structural) | PASS (offline structural) | Packaged project passed offline structural validation; live Gradle/browser validation requires approved environment
CopyDOM | ENABLED | ENABLED | Suite-wide CopyDOM / AutoDebug artifact lifecycle
AutoDebug | ENABLED | ENABLED | Central AutoDebugManager used by both scenarios
Recovery | ENABLED | ENABLED | Bounded recovery through shared recovery infrastructure
Test data / scenario | HOME Happy Path | Yvonne Fisher / BristolWest E2E | Scenario-specific deterministic data retained
Runtime artifact path | build/artifacts/dom/home-functional/... + central DOM | build/artifacts/dom/<Class.test>/<execution-id>/ | HTML + metadata + debug summary / existing screenshots and traces
Environment routing | PASS | PASS | QA/UAT FastQuote routing validation passed
Selenium prohibited scan | PASS | PASS | No Selenium/WebDriver runtime usage reintroduced
Shared project test inventory | 2,373 @Test | 2,373 @Test | Integrated master project structural count
Shared Java file inventory | 411 Java files | 411 Java files | Integrated AUTO + HOME project
Essential resources | 8 verified | 8 verified | Immutable essential resources verified
Current migration status | FUNCTIONALLY INTEGRATED | FUNCTIONALLY INTEGRATED | Selenium → Playwright Java integration complete for the two target E2Es; live environment validation remains the next gate.
NEXT VALIDATION
Priority | HOME Component(s) | AUTO Component(s) | Description / Priority
1 | homeDomHappyPathE2E live-action validation | bristolWestE2EDeterministic live-action validation | Execute both independently in the approved environment with visible browser and capture final result.
2 | HOME interstitial / review-quote recovery | AUTO Knockout / retrieve / spinner recovery | Keep CopyDOM + AutoDebug enabled and validate only state-aware recovery.
3 | HOME regression protection | AUTO regression protection | Rerun both target E2Es after shared framework, state detector, navigation, or recovery changes.
CURRENT RISKS / BLOCKERS
Component | HOME | AUTO | Required action
Inconvenience Page | HIGH | HIGH | Detect it immediately, capture CopyDOM, use bounded recovery/Try Again when available, and classify environment interruption separately from code defects.
Knockout Page | HIGH | HIGH | Preserve state-aware Knockout detection and recovery; for AUTO validate quote retrieval/resume before continuing the deterministic flow.
Farmers UI instability | HIGH | HIGH | Use semantic locators, conditional waits, state detection and CopyDOM. Avoid fixed sleeps and brittle selectors because UI timing/transitions are highly unstable.
PROJECT-WIDE VALIDATION
Metric | HOME / AUTO value | Status | Note
Master integration | AUTO + HOME | PASS | AUTO source preserved and HOME integrated on the same Playwright Java framework.
Target E2E coverage | 2 primary E2Es | PASS | homeDomHappyPathE2E + bristolWestE2EDeterministic are the two acceptance scenarios tracked on this dashboard.
Framework / diagnostics | Playwright Java + CopyDOM + AutoDebug + Recovery | PASS | Shared runtime provides browser lifecycle, DOM capture, debugging and bounded recovery without reintroducing Selenium/WebDriver.

## Migration Status
HOME / AUTO Migration Status — ffq-master-playwright
Category | Class / File | Method / Element (Playwright Target) | Selenium Method (Original / Current) | Status | Notes | Conversion Plan | Plan Start Date | Plan End Date | Total Days Expected | Actual Start Date | Actual End Date | Total Effort Days | Comments
Test Lifecycle | AutomationFramework.java | startPlaywrightTest(Method) | Selenium @BeforeMethod WebDriver setup | ✅ CONVERTED | PlaywrightSession starts test and binds Page/Context runtime. | No action required; maintain Playwright lifecycle hooks. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Test Lifecycle | AutomationFramework.java | finishPlaywrightTest(ITestResult) | Selenium @AfterMethod teardown/screenshot hooks | ✅ CONVERTED | Playwright final screenshot and trace lifecycle managed in AfterMethod. | No action required; maintain failure status capture. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Test Lifecycle | AutomationFramework.java | closePlaywrightWorker() | Selenium driver.quit() worker cleanup | ✅ CONVERTED | Thread-scoped Playwright worker shutdown replaces WebDriver quit. | No action required. | 18 | 18 | 18 | 18 | 18 | 18 | 18
@Test Methods | HomeHappyPathE2ETest.java | homeDomHappyPathE2E() | HOME Selenium-era Happy Path | ✅ INTEGRATED | HOME acceptance E2E integrated on shared AutomationFramework/PlaywrightSession; CopyDOM + AutoDebug + recovery retained. | Run live in approved environment; collect repeatability evidence. | 18 | 18 | 18 | 18 | 18 | 18 | Primary HOME E2E for this Home/Auto report.
@Test Methods | BindOneUIEndToEndTest.java | bristolWestE2EDeterministic() | AUTO Selenium-era deterministic bind flow | ✅ INTEGRATED | Known-working BristolWest deterministic flow integrated; applicant Yvonne Fisher; central CopyDOM/AutoDebug/Recovery preserved. | Run live in approved environment; validate Knockout/retrieve recovery and collect repeatability evidence. | 18 | 18 | 18 | 18 | 18 | 18 | Primary AUTO E2E for this Home/Auto report.
Framework | AutomationFramework.java / PlaywrightSession.java | Shared Playwright lifecycle | Selenium/WebDriver lifecycle | ✅ CONVERTED | HOME and AUTO reuse the same Playwright Java lifecycle and central diagnostic/recovery framework. | Maintain shared compatibility; rerun both target E2Es after framework changes. | 18 | 18 | 18 | 18 | 18 | 18 | Project-wide validation: 2,373 @Test annotations, 411 Java files, 8 verified essential resources.
@Test Methods | SaveAndRetrieveHomeQuoteScenarios.java | saveAndRetrieveHomeQuotes(ApplicantHome) | Legacy Selenium save/retrieve journey | ✅ CONVERTED | Uses Playwright Home pages and retrieve flow methods. | No Selenium migration work pending for this method. | 18 | 18 | 18 | 18 | 18 | 18 | DataProvider currently yields 0 rows in default regression config.
@Test Methods | StateScenarios.java | validateStateForHome(State) | Legacy Selenium state validation | ✅ CONVERTED | Playwright path across Landing/Home/Knockout validation pages. | No Selenium migration work pending for this method. | 18 | 18 | 18 | 18 | 18 | 18 | Invocation count driven by stateValidation worksheet rows.
@Test Methods | StateScenarios.java | validateStateForLegacyHomeUsingAOR(ApplicantHome) | Legacy Selenium AOR state check | ✅ CONVERTED | Playwright path; local-only execution guard still present. | Keep Playwright path; remove local-only guard only if approved. | 2026-08-08 | 2026-08-12 | 5 | 18 | 18 | 18 | 18
@Test Methods | HomeLocatorContractTests.java | validatesOneUiHomeContractMarkers() | N/A (new contract assertion) | ✅ CONVERTED | Pure Java fixture assertions; no Selenium runtime dependency. | No Selenium migration work pending for this method. | 18 | 18 | 18 | 18 | 18 | 18 | Single invocation test.
DataProviders | DataProviders.java | applicantHome(Method) | Selenium-era Home data source selection | ✅ CONVERTED | Provider is Java/Excel based; no Selenium API use. | Populate legacy-home state list to enable invocations. | 2026-08-08 | 2026-08-12 | 5 | 18 | 18 | 18 | 18
DataProviders | DataProviders.java | applicantHomeErrorValidation() | Selenium-era Home error-row provider | ✅ CONVERTED | Provider returns ApplicantHome filtered by errorScenario=DISABLED. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
DataProviders | DataProviders.java | aorHomeApplicant(Method) | Selenium-era AOR provider/filtering | ✅ CONVERTED | Provider filters monetized legacy states and optional home.case selectors. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
DataProviders | DataProviders.java | getRetrieveQuoteHome(Method) | Selenium-era retrieve provider | ✅ CONVERTED | Provider uses Excel + state filters; no Selenium API use. | Populate legacy-home state list to enable invocations. | 2026-08-08 | 2026-08-12 | 5 | 18 | 18 | 18 | 18
DataProviders | SqlDataProviders.java | state(Method) [StatesDataProvider] | Selenium-era state iteration provider | ✅ CONVERTED | Provider is Java/Excel based with randomized ZIP assignment. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
DataProviders | DataProviders.java | getListOfLegacyHomeStates(String) | Legacy state gate used by Home providers | ✅ CONVERTED | Method currently returns empty list, causing zero rows for some Home tests. | Populate supported legacy home states per environment. | 2026-08-08 | 2026-08-12 | 5 | 18 | 18 | 18 | 18
DataProviders | DataProviders.java | getListOfLegacyHomeMonetizedStates(String) | Legacy monetized-state resolution | ✅ CONVERTED | Returns NJ/NY for regression/test routing fallback. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | LandingPage.java | enterLandingPageDataAndContinue(String,String) | driver.findElement/sendKeys/click flow | ✅ CONVERTED | Uses Playwright Locator/page interactions for landing submission. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | Shared page used by HOME runtime path.
Home Pages | YourInfoPageHome.java | enterYourInfoAndContinue(ApplicantHome,boolean,FarmersSoftAssert) | Selenium Your Info entry & continue | ✅ CONVERTED | Playwright locators, waits, and page transition checks. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | PropertyPage.java | enterPropertyInfo(ApplicantHome,FarmersSoftAssert) | Selenium Property page interactions | ✅ CONVERTED | Playwright-based field entry and continue action. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | ChooseYourCoveragePage.java | enterChooseYourCoveragePage(ApplicantHome,FarmersSoftAssert) | Selenium coverage package selection | ✅ CONVERTED | Playwright locators and dropdown/radio interactions. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | QuotePageHome.java | enterQuotePage(ApplicantHome,FarmersSoftAssert) | Selenium quote page continuation | ✅ CONVERTED | Playwright continuation path and quote-page branching logic. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | ThankYouPage.java | verifyThankYouPageContent(ApplicantHome,FarmersSoftAssert) | Selenium final-page assertions | ✅ CONVERTED | Assertions are executed through Playwright-derived page objects. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | YourInfoPageHome.java | onYourInfoPageHome() | Selenium isOn page guard | ✅ CONVERTED | Visibility/path detection uses Playwright locators. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Home Pages | KnockoutInconveniencePage.java | isQuoteKnockedOut() | Selenium knockout presence checks | ✅ CONVERTED | Knockout/inconvenience detection uses Playwright locators. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Navigation Helpers | QuoteScenarios.java | dispatchHomeFlowForQuoteCreation(ApplicantHome,FarmersSoftAssert) | Legacy Selenium branch routing | ✅ CONVERTED | HomeFlowRouter-based Playwright flow dispatch (LEGACY/ONE_UI/etc.). | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Navigation Helpers | AceHomeNavigationHelper.java | resumeFromAngularComponent(String) | Selenium URL/title resume logic | ✅ CONVERTED | Component-based resume routing for OneUI flow. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Navigation Helpers | AceHomeNavigationHelper.java | navigateToAceHomeContactInfoPage(ApplicantAceHome,String,String) | Selenium click/wait transition from About You | ✅ CONVERTED | Playwright transition wrapped with HomeRecoveryManager. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Navigation Helpers | AceHomeNavigationHelper.java | navigateToAceHomeReviewQuotePage(ApplicantAceHome,String,String) | Selenium chained navigation to review quote | ✅ CONVERTED | Playwright chained navigation via Ace HRC page objects. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Helper Classes | HomeFlowRouter.java | detect() | N/A (new Playwright flow detector) | ✅ CONVERTED | Inspects URL/components/headings/buttons using Playwright Page/Locator. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Helper Classes | HomeRecoveryManager.java | performRecoverableNavigation(...) | N/A (new Playwright recovery helper) | ✅ CONVERTED | Performs Try again recovery using Playwright role locator. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | Recovery exhausted can still fail functional execution.
BasePage Shared | BasePage.java | waitForSpinnerToBeGone() | Selenium spinner wait utilities | ✅ CONVERTED | Shared wait utility now Playwright-based and used by HOME pages. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
BasePage Shared | BasePage.java | clearOutFieldUsingBackSpace(Locator) | Selenium clear/sendKeys backspace helper | ✅ CONVERTED | Shared field-clear helper accepts Playwright Locator. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
BasePage Shared | BasePage.java | clickContinueButton() | Selenium click wrapper | ✅ CONVERTED | Shared continue click wrapper uses Playwright scroll+click. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Config | build.gradle | homeTest task include com/farmers/ffq/home/**/*.class | Selenium-specific suite wiring | ✅ CONVERTED | Dedicated HOME task exists and targets Home package classes only. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18
Config | build.gradle | systemProperties passthrough for home.case.zip/home.case.index | Selenium-era JVM arg wiring | ✅ CONVERTED | HOME selector properties are passed to Test JVM for deterministic AOR row selection. | No Selenium migration work pending. | 18 | 18 | 18 | 18 | 18 | 18 | 18

## Column Legend
Column Definitions & Status Legend
Column | Definition
Category | Migration category for HOME-only execution surface (Test Lifecycle, @Test Methods, DataProviders, Home Pages, BasePage Shared, Navigation Helpers, Helper Classes, Config).
Class / File | Exact Java class or configuration file in the repository.
Method / Element (Playwright Target) | Specific method/element tracked as migration unit for HOME execution.
Selenium Method (Original) | Original Selenium pattern/behavior replaced or represented by current implementation.
Status | ✅ CONVERTED, ⚠ PARTIAL, ❌ SELENIUM classification.
Notes | Current technical behavior and runtime relevance.
Conversion Plan | Actionable migration/completion steps for this unit.
Plan Start Date | Planned start date for pending work.
Plan End Date | Planned completion date for pending work.
Total Days Expected | Estimated duration for planned work item.
Actual Start Date | Verified actual start date (blank when unverifiable).
Actual End Date | Verified actual completion date (blank when unverifiable).
Total Effort Days | Verified actual effort days (blank when unverifiable).
Comments | Additional execution impact, blockers, or context.
STATUS LEGEND
✅ CONVERTED | Method is fully Playwright. No Selenium imports/calls in HOME runtime execution path.
⚠ PARTIAL | Method has Playwright implementation but still has Selenium fallback/dependency or inconsistent runtime injection.
❌ SELENIUM | Method still uses Selenium exclusively in HOME runtime path and must be migrated.
MIGRATION PRIORITY ORDER
1. CRITICAL BLOCKERS
2. CONSTRUCTOR FIXES
3. isOnXxxPage() / visibility methods
4. NAVIGATION METHODS
5. INTERACTION METHODS
6. SHARED BasePage METHODS
7. XML & GRADLE